## Exec Summary-A
Executive Summary
[5 empty] | Scheme Code No. : |  |  |  | A
Amount in Rs. Lakhs
State |  |  | JHARKHAND |  | Total Project Cost
Name of Power Utility |  |  | JSEB |  | Capital Subsidy
Name of District |  |  | Bokaro |  | Loan
No. of Blocks |  |  | 6 |  | Other source of funding, if any
Total Population of the area |  |  | 1507572 |  | Revenue Subsidy,
( if any, committed by State Govt. )
Total Geographical Area (SqKm) |  |  |  |  | Scheme Implementation Period
Whether in Forest Area (Yes/No) |  |  | No |  | (a) Start (Proposed)
(b) Completion (Proposed)
Mode of Implementation :
Implementing Authority / Agency : |  |  | JSEB
Consultant :
Status of Village Electrification
Total No. of Inhabited Villages |  |  | No. of villages electrified as on | % Electrification | Balance no. of villages to be electrified as on |  | No of villages covered in the scheme*
[7 empty] | Electrified | Unelectrified
1 |  |  | 2 | 3 | 4 |  | 5 | 6
749 |  |  | 621 | 82.9105 | 128 |  | 0 | 23
Status of Electrification of Village Habitations(Hemlets/Dhani/Tola/Majra/Kara)
Total No. of Village Habitations |  |  | No. of Village Habitations electrified as on |  | % Electrification |  | Balance no. of Village Habitations to be electrified as on
1 |  |  | 2 |  | 3 |  | 4
1630 |  |  | 1336 |  | 81.9632 |  | 264
Status of Rural Household Electrification (Including BPL households)
Total No. of Households |  |  | No. of Households electrified as on |  | % Electrification |  | Balance no. of households to be provided access to electrycity under the present project
1 |  |  | 2 |  | 3 |  | 4
89563 |  |  | 60007 |  | 66.9998 |  | 29556
Status of BPL (Below Poverty Line) Household Electrification
Total No. of BPL Households |  |  | No. of BPL Households electrified as on |  | % Electrification |  | Balance no. of BPL households to be electrified under the present project
Electrification of Public places / services
Public places / services |  |  | Total |  | Proposed to be electrified under present scheme |  | Balance
Schools |  |  | 20 |  | 20 |  | 0
Pachayat Office |  |  | 8 |  | 8 |  | 0
Health Centres |  |  | 3 |  | 3 |  | 0
Dispensaries
Community Centres
Others like street lights etc. (Pl. specify)
Proposed number of connections to be released under present project
Category --> | Domestic (other than BPL) | Domestic (BPL) | Commercial | Agriculural | Small Industrial | Water Works | Others (School+Panchyat+H.C)
No. of Services | 4608 | 7124 | 63 | 81 |  |  | 31
Details of on-going initiatives (projects) in the present project area
(Ref. : Para 5.1 (d) of Guidelines for project formulation)
Sr. No. | Name of Project | District | No. of Blocks Covered | No. of un-electrified villages to be electrified, if any | Name of Programme * | Funding Agency ** | Date of Start of project | Scheduled Date of Completion
1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11
1 | State Plan | Bokaro | 6 | 23
2
3
| Total |  | 6 | 23 | 0 | 0 | 0 | 0

## Scope of Work-abstract-B
Abstract - Scope of work and estimated cost
State : Jharkhand |  |  | Scheme Code No. :
District : | [6 empty] | B
Sr.No. | Item of Work | Specifications | Unit | Ref. No. for detailed cost data | Unit Cost | Total Quantity | Total Cost
[5 empty] | Rs.Lakh |  | Rs.Lakh
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
1 | New 11 KV Lines WithWeasel ACSR- 3 Ph | On 8 Mtr., 200 lbs PSC Pole | Circuit Km. | 2010-11 with 10% hike | 2.493 | 84.61 | 210.9327
2 | New Distribution sub-stations 25 KVA (3 ph) with meter | 11/ 0.4 KV | Nos. | 2010-11 with 10% hike | 2.051 | 203 | 416.353
3 | New LT Lines 3 Ph AB cable | On 8 Mtr., 200 lbs PSC Pole,Vertical Formation | Km. | 2010-11 with 10% hike | 1.57 | 67.39 | 105.8023
4 | New LT Lines 1 Ph AB Cable | On 8 Mtr., 200 lbs PSC Pole,Vertical Formation | Km. | 2010-11 with 10% hike | 2.01 | 39.71 | 79.8171
5 | BPL beneficiaries | Electromechanical Meter | Nos. | 2010-11 with 10% hike | 1.08 | 0 | 0
| Total (1+2+3+4+5) |  |  |  | 9.204 | 394.71 | 812.9051
Note: | All prices are including installation/ Construction/ Erection and Commissioning charges | [5 empty] | #REF!

## Scheme Area Details(Block)- C1a
Blockwise Details On Present Status of Electrification of Villages & Habitations
C - 1a
State : Jharkhand
Name of District & Census Code : | [9 empty] | Scheme Code No. :
Sr.No. | Name of Block | Census Code (2001) | Total Population | Total Area | Status of Electrification of Vllages |  |  |  | Status of Electrification of Habitations (Hamlet/Dhani/Tola/Majra/Kara) |  |  |  | No. of villages electrified with non-conventional energy sources, if any
[5 empty] | Total No. of villages | No. of villages electrified as on | % Electrification | Balance no. of villages to be electrified | Total No. of Village Habitations | No. of Village Habitations electrified as on | % Electrification | Balance no. of Village Habitations to be electrified as on
|  |  | Nos. | Sq.Km | Nos. | Nos. | % | Nos. | Nos. | Nos. | % | Nos. | (Proposed)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Gomia |  |  |  | 135 | 121 | 89.6296 | 14 | 295 | 271 | 91.8644 | 24
2 | Jaridih |  |  |  | 42 | 30 | 71.4286 | 12 | 102 | 72 | 70.5882 | 30
3 | Petarwar |  |  |  | 65 | 48 | 73.8462 | 17 | 145 | 109 | 75.1724 | 36
4 | Nawadih |  |  |  | 69 | 58 | 84.058 | 11 | 172 | 133 | 77.3256 | 39
5 | Bermo |  |  |  | 10 | 8 | 80 | 2 | 23 | 21 | 91.3043 | 2
6 | Chas |  |  |  | 144 | 131 | 90.9722 | 13 | 306 | 278 | 90.8497 | 28
| Total |  |  |  | 465 | 396 | 85.1613 | 69 | 1043 | 884 | 84.7555 | 159

## Scheme Area Details(Block)-C1b
C - 1b
Blockwise Details On Present Status of Rural Household Electrification
State : Jharkhand
Name of District & Census Code : | [5 empty] | Scheme Code No.
Sr.No. | Name of Block | Census Code (2001) | Status of Rural Households (RHH) Electrification - As per Census 2001 (Including BPL households) |  |  |  | Status of Below Powerty Line Households (BPL HH) Electrification
|  |  | Total No. of RHH | No. of RHH electrified as on | % Electrification | Balance no. of RHHs to be electrified | Total No. of BPL HH | No. of BPL HH electrified as on | % Electrification | Balance no. of BPL HH to be electrified
|  |  | Nos. | Nos. | % | Nos. | Nos. | Nos. | % | Nos.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
1 | Gomia |  | 16566 | 10768 | 65.0006 | 5798 |  | 3988
2 | Jaridih |  | 10143 | 6897 | 67.9976 | 3246 |  | 886
3 | Petarwar |  | 14204 | 9800 | 68.9946 | 4404 |  | 4032
4 | Nawadih |  | 19763 | 13241 | 66.9989 | 6522 |  | 2955
5 | Bermo |  | 3782 | 2496 | 65.9968 | 1286 |  | 146
6 | Chas |  | 25105 | 16805 | 66.9389 | 8300 |  | 1422
| Total |  | 89563 | 60007 | 66.9998 | 29556 | 0 | 13429

## Scheme Area Details(Block)- C2
Blockwise Details of Existing Consumers | [16 empty] | C - 2
State : Jharkhand
Name of District & Census Code : | [13 empty] | Scheme Code No. :
Sr.No. | Name of Block | Census Code (2001 | Category wise no. of consumers and connected load | [8 empty] | Categorywise average sale of energy (Kwh) and revenue per annum
|  |  | Dom. | Kutir Jyoti / BPL HH | Comm. | Ag. | Small Ind. | Water Works | Street Lights | Others _______ | Total | Dom. | Kutir Jyoti / BPL HH | Comm. | Ag. | Small Ind. | Water Works | Street Lights | Others _______ | Total
|  |  | No./KW | No./KW | No./KW | No./KW | No./KW | No./KW | No./KW | No./KW | No./KW | Kwh / Rs | Kwh / Rs | Kwh / Rs | Kwh / Rs | Kwh / Rs | Kwh / Rs | Kwh / Rs | Kwh / Rs | Kwh / Rs
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
1 | Gomia |  | 15042 | 876 | 950 | 6 | 62 | 18 | 4 |  | 16958
2 | Jaridih |  | 9601 | 2725 | 280 | 25 | 35 | 4 | 0 |  | 12670
3 | Petarwar |  | 7214 | 3884 | 153 | 15 | 20 | 3 | 0 |  | 11289
4 | Nawadih |  | 5865 | 320 | 664 | 4 | 32 | 2 | 0 |  | 6887
5 | Bermo |  | 8103 | 520 | 170 | 5 | 45 | 2 | 0 |  | 8845
6 | Chas |  | 16584 | 1824 | 3035 | 13 | 270 | 16 | 7 |  | 21749
7
8
9
Note : 1. The above informatiom is required only for RURAL AREA
2. The above informatiom is required for all the blocks in a district

## Scheme Area Details(Block)- C3
Blockwise Details of Sub-stations and Lines located in the block
C - 3
State : Jharkhand
Name of District & Census Code : | [9 empty] | Scheme Code No. :
Sr. No. | Name of Block | Census Code (2001) | Existing Sub-stations and Lines located in each block
|  |  | 132/33 KV Sub-stations |  | 33/11 KV Sub-stations |  | Length of 33 KV Line | Total No. of 11 KV feeders | Length of 11 KV Lines | Distribution Sub-stations |  | Total No. of LT feeders | Length of LT Lines
|  |  | No. of sub-stations | Total Power Transformer Capacity | No. of sub-stations | Total Power Transformer Capacity |  |  |  | No. of sub-stations | Total Dist. Transformer Capacity
|  |  | Nos. | MVA | Nos. | MVA | Kms | No. | Kms | No. | MVA | No. | Kms
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Gomia |  |  |  | 3 | 43.15 | 14.5 | 7 | 197 | 423 | 28.568 | 495 | 336
2 | Jaridih |  |  |  | 1 | 20 | 18 | 3 | 241 | 260 | 20.391 | 295 | 275
3 | Petarwar |  |  |  | 1 | 6.3 | 20 | 2 | 85 | 180 | 7.123 | 215 | 106
4 | Nawadih |  |  |  | 1 | 6.3 | 33 | 2 | 125 | 145 | 10.115 | 163 | 115
5 | Bermo |  |  |  | 0 | 0 | 0 | 0 | 134 | 158 | 11.106 | 175 | 127
6 | Chas |  |  |  | 1 | 50 | 25 | 12 | 497 | 716 | 81.11 | 740 | 731
Total

## un-electrified villC-7
Blockwise Villagewise details of un-electrified villages to be electrified under present scheme
C - 7
State : Jharkhand
Name of District & Census Code : | [8 empty] | Scheme Code No. :
Sr.No. (Block) | Name of Block | Census Code (2001) | Sr.No. (Village) | Name of De-electrified Village | Census Code (2001) | Total no. of Rural Households | Total no. of BPL Rural Households | Population | Area (Sq.Km.) | Whether SC/ST/ Tribal Village | Distance from Nearest 33/11 KV sub-station (Kms) | Distance from Nearest 11 KV Line (Kms) | Public Places / Services - No. of
[13 empty] | Schools | Panchayat Office | Health Centres | Community Centres | Others (Pl. specify)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
1 | 2: Gomia; 4: 1; 5: Dhawaiya & its 9 tola; 6: 2368600; 7: 325
|  |  | 2 | Badkipunnu & its 07 tola | 2368900 | 340
|  |  | 3 | Ashnabera Badki Chichri | 2371800 | 45
2 | 2: Jaridih; 4: 1; 5: Kashidih; 6: 2389100; 7: 49
|  |  | 2 | Gopalpur & its Tola | 2391800 | 175
|  |  | 3 | Chilgadha & its tola | 2390900 | 110
|  |  | 4 | Bhaski & its tola | 2392300 | 360
|  |  | 5 | Kamalpur & its tola | 2392700 | 180
|  |  | 6 | Aaraju & its tola | 2392600 | 185
|  |  | 7 | Bara Kenduadih Khuntri | 2388900 | 42
3 | 2: Peterwar; 4: 1; 5: Ulgadda & its tola; 6: 2379400; 7: 625
|  |  | 2 | Rajak Tola Darid | 2381300 | 39
|  |  | 3 | Aake & its tola | 2377100 | 60
|  |  | 4 | Birhorbera Angwali | 2380400 | 36
|  |  | 5 | Bhulan Khadko | 2380700 | 72
|  |  | 6 | Durgapur & its tola | 2384600 | 460
4 | 2: Nawadih; 4: 1; 5: Kurpania; 6: 2356900; 7: 62
|  |  | 2 | Argamo | 2357000 | 18
|  |  | 3 | Bridih | 2356800 | 160
|  |  | 4 | Ghusko | 2356600 | 78
5 | 2: Bermo; 4: 1; 5: Bansi; 6: 2356500; 7: 270
|  |  | 2 | Muchro | 2356400 | 130
6 | 2: Chas; 4: 1; 5: Yogidih; 6: 2395400; 7: 54
| Grand Total |  |  |  |  | 3875
Note :- | 2: Habitation wise details are not required to be furnished in Col 10, 11, 12 & 13

## Scheme Proposal (Block)- D1a
Scheme Proposal : Blockwise electrification of Villages and Habitations proposed under present scheme
D - 1a
State : Jharkhand
Scheme Code No. :
Name of District & Census Code :
Sr. No. | Name of Block | Census Code (2001) | Village Electrification |  |  | Status of Electrification of Habitations (Hamlet/Dhani/Tola/Majra/Kara)
|  |  | Balance no. of villages to be electrified as on | Proposed No. of villages to be electrified under persent scheme | No. of villages to be electrified under other schemes (not covered in present scheme) | Balance no. of habitations to be electrified | Proposed No. of habitations to be electrified | No. of habitations to be electrified under other schemes (not covered in present scheme)
|  |  | Nos. | Nos. | Nos. | Nos. | Nos. | Nos.
1 | 2 | 3 | 4 | 5 | 6 | 4 | 5 | 6
1 | Gomia |  | 14 | 3 | 11 | 24 | 7 | 17
2 | Jaridih |  | 12 | 7 | 5 | 30 | 14 | 16
3 | Petarwar |  | 17 | 6 | 11 | 36 | 15 | 21
4 | Nawadih |  | 11 | 4 | 7 | 39 | 17 | 22
5 | Bermo |  | 2 | 2 | 0 | 8 | 8 | 0
6 | Chas |  | 20 | 1 | 19 | 28 | 2 | 26
| Total |  | 76 | 23 | 53 | 165 | 63 | 102

## Scheme Proposal (Block)- D1b
Scheme Proposal : Blockwise electrification of rural households and BPL households and Public places / services proposed under present scheme
D - 1b
State : Jharkhand
Name of District & Census Code : | [9 empty] | Scheme Code No. :
Sr. No. | Name of Block | Census Code (2001) | Rural Households (RHH) Electrification (including BPL households) |  |  | Below Powerty Line Households (BPL HH) Electrification |  |  | Electrification of Public places / services
|  |  | Balance no. of RHH to be provided access to electriicty | Proposed No. of connections to be released to RHH | Balance no. of RHH to be connected in future | Balance no. of BPL HH to be electrified | Proposed No. of connections to be released to BPL HH | Balance no. of BPL HH to be connected in future, if any (Pl. also indicate reasons)* | Schools | Panchayat Office | Health Centres | Other ___________ (Pl. Specify)
|  |  | Nos. | Nos. | Nos. | Nos. | Nos. | Nos. | Nos. | Nos. | Nos. | Nos.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Gomia |  | 4536 | 3220 | 1316 |  |  |  | 3 | 1 | 0
2 | Jaridih |  | 3670 | 2135 | 1535 |  |  |  | 6 | 2 | 1
3 | Petarwar |  | 3213 | 2110 | 1103 |  |  |  | 6 | 2 | 1
4 | Nawadih |  | 5312 | 3856 | 1456 |  |  |  | 4 | 2 | 1
5 | Bermo |  | 935 | 580 | 355 |  |  |  | 1 | 1 | 0
6 | Chas |  | 2320 | 1912 | 408 |  |  |  | 0 | 0 | 0
| Total |  | 19986 | 13813 | 6173 | 0 | 0 | 0 | 20 | 8 | 3 | 0

## Scheme Pro. (Un-elec_Villag)-D3
Scheme Proposal : Blockwise Villagewise details of electrification of rural houseolds, BPL households and public services
D - 3
State : Jharkhand
Name of District & Census Code : | [9 empty] | Scheme Code No. :
Sr.No. (Block) | Name of Block | Census Code (2001) | Sr.No. (Village) | Name of Village/ Habitation (Hamlet/Dhani/Majra/Kara/Dalit Basti) | Census Code (2001) |  | Electrification of Habitations (Hamlet/Dhani/Tola/Majra/Kara) |  |  | Rural Households (RHH) Electrification |  |  | Below Powerty Line Households (BPL HH) Electrification |  |  | Electrification of Public places / services
[6 empty] | PS No. | Balance no. of habitations to be electrified | Proposed No. of habitations to be electrified | Balance no. of habitations to be electrified in future | Balance no. of RHH to be provided access to electriicty | Proposed No. of connections to be released to RHH | Balance no. of RHH to be connected in future | Balance no. of BPL HH to be electrified | Proposed No. of connections to be released to BPL HH | Balance no. of BPL HH to be connected in future, if any (Pl. also indicate reasons)* | Schools | Panchayat Office | Health Centres | Other ________ (Pl. Specify)
1 | 2 | 3 | 4 | 5 | 6 | xyz | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
1 | Gomia |  | 1 | Dhawaiya & its 9 tola | 2368600 |  | 9 | 9 | 0 | 325 | 325 | 0 |  |  |  | 1 | 0
|  |  | 2 | Badkipunnu & its 07 tola | 2368900 |  | 7 | 7 | 0 | 340 | 340 | 0 |  |  |  | 1 | 1
|  |  | 3 | Ashnabera Badki Chichri | 2371800 |  | 2 | 2 | 0 | 45 | 45 | 0 |  |  |  | 1 | 0
2 | Jaridih |  | 1 | Kashidih | 2389100 |  | 2 | 2 | 0 | 49 | 49 | 0 |  |  |  | 0 | 0
|  |  | 2 | Kochgodda of Bandhid | 2391800 |  | 6 | 6 | 0 | 175 | 175 | 0 |  |  |  | 1 | 0
|  |  | 3 | Chilgadha & its tola | 2390900 |  | 4 | 4 | 0 | 110 | 110 | 0 |  |  |  | 1 | 0
|  |  | 4 | Bhaski & its tola | 2392300 |  | 8 | 8 | 0 | 360 | 360 | 0 |  |  |  | 1 | 1
|  |  | 5 | Kamalpur & its tola | 2392700 |  | 6 | 6 | 0 | 180 | 180 | 0 |  |  |  | 1 | 0
|  |  | 6 | Aaraju & its tola | 2392600 |  | 6 | 6 | 0 | 185 | 185 | 0 |  |  |  | 1 | 1
|  |  | 7 | Bara Kenduadih Khuntri | 2388900 |  | 2 | 2 | 0 | 42 | 42 | 0 |  |  |  | 1 | 0
3 | Peterwar |  | 1 | Ulgadda & its tola | 2379400 |  | 16 | 16 | 0 | 625 | 625 | 0 |  |  |  | 1 | 1
|  |  | 2 | Rajak Tola Darid | 2381300 |  | 2 | 2 | 0 | 39 | 39 | 0 |  |  |  | 1 | 0
|  |  | 3 | Aake & its tola | 2377100 |  | 3 | 3 | 0 | 60 | 60 | 0 |  |  |  | 1 | 0
|  |  | 4 | Birhorbera Angwali | 2380400 |  | 2 | 2 | 0 | 36 | 36 | 0 |  |  |  | 1 | 0
|  |  | 5 | Bhulan Khadko | 2380700 |  | 2 | 2 | 0 | 72 | 72 | 0 |  |  |  | 1 | 0
|  |  | 6 | Durgapur & its tola | 2384600 |  | 10 | 10 | 0 | 460 | 460 | 0 |  |  |  | 1 | 1
4 | Nawadih |  | 1 | Kurpania | 2356900 |  | 2 | 2 | 0 | 62 | 62 | 0 |  |  |  | 1 | 0
|  |  | 2 | Argamo | 2357000 |  | 1 | 1 | 0 | 18 | 18 | 0 |  |  |  | 1 | 0
|  |  | 3 | Bridih | 2356800 |  | 4 | 4 | 0 | 160 | 160 | 0 |  |  |  | 1 | 1
|  |  | 4 | Ghusko | 2356600 |  | 2 | 2 | 0 | 78 | 78 | 0 |  |  |  | 1 | 1
5 | Bermo |  | 1 | Bansi | 2356500 |  | 8 | 8 | 0 | 270 | 270 | 0 |  |  |  | 1 | 1
|  |  | 2 | Muchro | 2356400 |  | 4 | 4 | 0 | 130 | 130 | 0 |  |  |  | 0 | 0
6 | Chas |  | 1 | Yogidih | 2395400 |  | 1 | 1 | 0 | 54 | 54 | 0 |  |  |  | 0 | 0
4581

## Scheme Pro.( Unelec_Village)-D4
Scheme Proposal : Villagewise Proposed Infrastructure
|  |  |  | Un-Electrified | [17 empty] | D - 4
State : Jharkhand
Name of District & Census Code : | [12 empty] | Scheme Code No. :
Sr.No. | Name of Block | Census Code of the Block (2001) | Sr.No. (Village) | Name of Village/ Habitation (Hamlet/Dhani/Majra/Kara/Dalit Basti) | Census Code (2001) |  | Proposed infrastructure | [13 empty] | Name of feeding 33/11 KV sub-stations | Name of concerned 11 KV Feeder
[6 empty] | PS No. | 33/11 KV S/S | Length of 33 kV line | Distribution Sub-stations | [5 empty] | Length of 11 KV Lines in Kms |  | No. of LT Feeders | Length of LT Lines
[9 empty] | Transformer Capacity (kVA) |  |  |  | 1-ph or 3ph | Total of Transformer capacity in KVA | Single Phase | Three Phase |  | Configuration (1-ph, 3/1-Ph etc.) | Length of LT Lines in kms
[7 empty] | No/MVA | kms | 10 | 16 | 25 | KVA |  |  |  |  | Nos. |  | 1-Ph | 3-Ph
1 | 2 | 3 | 4 | 5 | 6 | [6 empty] | 6 | 7 | 8 | 9 |  | 10 | 11 | 12 |  | 13 | 12
1 | Gomia |  | 1 | Dhawaiya & its 9 tola | 2368600 | [5 empty] | 18 |  | 3 Ph | 450 |  | 9.0 | 18 |  | 3.2 | 4.8 | Kuju | Kuju
|  |  | 2 | Badkipunnu & its 07 tola | 2368900 | [5 empty] | 18 |  | 3 Ph | 450 |  | 10.0 | 18 |  | 6 | 9 | Kuju | Kuju
|  |  | 3 | Ashnabera Badki Chichri | 2371800 | [5 empty] | 3 |  | 3 Ph | 75 |  | 1.0 | 3 |  | 0.4 | 0.6 | Kuju | Kuju
2 | Jaridih |  | 1 | Kashidih | 2389100 | [5 empty] | 3 |  | 3 Ph | 75 |  | 0.6 | 3 |  | 0.6 | 0.9 | Jaina | Kasmar
|  |  | 2 | Gopalpur & its tola | 2391800 | [5 empty] | 9 |  | 3 Ph | 225 |  | 3.6 | 9 |  | 1.6 | 2.4 | Jaina | Jaina
|  |  | 3 | Chilgadha & its tola | 2390900 | [5 empty] | 6 |  | 3 Ph | 150 |  | 3.0 | 6 |  | 2 | 3 | Jaina | Jaina
|  |  | 4 | Bhaski & its tola | 2392300 | [5 empty] | 12 |  | 3 Ph | 300 |  | 4.5 | 12 |  | 3.36 | 5.04 | Bagiyari | Khairachatar
|  |  | 5 | Kamalpur & its tola | 2392700 | [5 empty] | 9 |  | 3 Ph | 225 |  | 3.0 | 9 |  | 3 | 4.5 | Jaina | Jaina
|  |  | 6 | Aaraju & its tola | 2392600 | [5 empty] | 9 |  | 3 Ph | 225 |  | 2.5 | 9 |  | 2 | 3 | Bagiyari | Khairachatar
|  |  | 7 | Bara Kenduadih Khuntri | 2388900 | [5 empty] | 3 |  | 3 Ph | 75 |  | 1.2 | 3 |  | 1 | 1.5 | Jaina | Jaina
3 | Peterwar |  | 1 | Ulgadda & its tola | 2379400 | [5 empty] | 33 |  | 3 Ph | 825 |  | 12.0 | 33 |  | 5.4 | 8.1 | Kathara | Tenu
|  |  | 2 | Rajak Tola Darid | 2381300 | [5 empty] | 3 |  | 3 Ph | 75 |  | 1.6 | 3 |  | 0.6 | 0.9 | Chargi | Petarwar
|  |  | 3 | Aake & its tola | 2377100 | [5 empty] | 4 |  | 3 Ph | 100 |  | 1.2 | 4 |  | 2.6 | 3.9 | Chargi | Ordana
|  |  | 4 | Birhorbera Angwali | 2380400 | [5 empty] | 3 |  | 3 Ph | 75 |  | 1.6 | 3 |  | 0.6 | 0.9 | Kathara | Phusro
|  |  | 5 | Bhulan Khadko | 2380700 | [5 empty] | 4 |  | 3 Ph | 100 |  | 3.0 | 4 |  | 1.6 | 4 | Chargi | Petarwar
|  |  | 6 | Durgapur & its tola | 2384600 | [5 empty] | 24 |  | 3 Ph | 600 |  | 6.0 | 24 |  | 1.2 | 6.3 | Jaina | Kasmar
4 | Nawadih |  | 1 | Kurpania | 2356900 | [5 empty] | 4 |  | 3 Ph | 100 |  | 2.75 | 4 |  | 0.9 | 1.35 | Gomia | Narki
|  |  | 2 | Argamo | 2357000 | [5 empty] | 1 |  | 3 Ph | 25 |  | 0.90 | 1 |  | 0.2 | 0.3 | Gomia | Narki
|  |  | 3 | Bridih | 2356800 | [5 empty] | 6 |  | 3 Ph | 150 |  | 3.0 | 6 |  | 1 | 1.5 | Gomia | Narki
|  |  | 4 | Ghusko | 2356600 | [5 empty] | 4 |  | 3 Ph | 100 |  | 2.5 | 4 |  | 0.5 | 0.75 | Gomia | Narki
5 | Bermo |  | 1 | Bansi | 2356500 | [5 empty] | 14 |  | 3 Ph | 350 |  | 7.16 | 14 |  | 1 | 3 | Kharpitto | Uparghat
|  |  | 2 | Muchro | 2356400 | [5 empty] | 7 |  | 3 Ph | 175 |  | 3.50 | 7 |  | 0.3 | 1 | Kharpitto | Uparghat
6 | Chas |  | 1 | Yogidih | 2395400 | [5 empty] | 4 |  | 3Ph | 100 |  | 1.0 | 4 |  | 0.65 | 0.65 | Chas | Pindrajora
[5 empty] | 1329 | 547 | 355
[5 empty] | 219 | 143 | 80
[5 empty] | 273 | 197 | 2
[5 empty] | 1821 | 887 | 437

## Scheme Pro.(unelec_villag)-D-5
Scheme Proposal : Village-wise category-wise proposed no. of connections
State : Jharkhand
Name of District & Census Code : | [9 empty] | Scheme Code No. :
Sr.No. | Name of Block | Census Code (2001) | Sr.No. (Village) | Name of Village/ Habitation (Hamlet, Majra, Dhani,Kara, Dalit Basti) | Census Code (2001) |  | Proposed No. of Connections and Connected Load
[6 empty] | PS No. | Domestic (Other than BPL) |  | Domestic (BPL) |  | Commercial |  | Agriculture |  | Small Industries |  | Others (Pl. Specify) |  | Total
[7 empty] | No. | KW | No. | KW | No. | KW | No. | KW | No. | KW | No. | KW | No. | KW
1 | 2 | 3 | 4 | 5 | 6 |  | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
1 | Block - 1 |  | 1 | Village -1 (Block - I)
|  |  | (i) | Habitation - 1 (Vill - 1)
|  |  | (ii) | Habitation - 2(Vill - 1)
Sub-Total (Vill - 1)
|  |  | 2 | Village - 2 (Block - 1)
|  |  | (i) | Habitation - 1 (Vill - 2)
|  |  | (ii) | Habitation - 2(Vill - 2)
Sub-Total (Vill - 2)
Sub - Total (Block - 1)
2 | Block - 2 |  | 1 | Village -1 (Block - 2)
|  |  | (i) | Habitation - 1 (Vill - 1)
|  |  | (ii) | Habitation - 2(Vill - 1)
Sub-Total (Vill - 1)
|  |  | 2 | Village - 2 (Block - 2)
|  |  | (i) | Habitation - 1 (Vill - 2)
|  |  | (ii) | Habitation - 2(Vill - 2)
Sub-Total (Vill - 2)
Sub - Total (Block - 2)
Grand Total